## Sheet1
ID | Todos | Status | Notes | Date: | 2018-03-15
| Physical UI Design | Ongoing
| Battery charge view in Hola App | Closed
| How to respond to Low Battery? | Closed
| Antenna | Closed
| Restore Default option in App | Open
| Only Forward if mutual buddies | Closed
| Learn OAuth2.0 and RFC6739 | Rejected
| Robustness against server restart | Ongoing | Needs more testing
| Robustness against intercom restart | Ongoing | Needs more testing
| Permant secret key | Closed
| Power switch circuit | Open
| Improve audio quality | Ongoing
| Assume message link is lossy | Closed
| Device setup and configuration via Android App | Closed
| Device setup and configuration via OSX App | Open
| Unique return codes. Use per-module return code base. | Closed
| Echo Cancelling | Open
| Intranet Mode | Open
| Voltage Regulation | Open
| Authentication and Security | Closed
| Battery support | Closed
| Remove my_name setting | Rejected | Keeping my_name because it's local persistent storage. The particle name is kept in the cloud.
| Contribute code library to Particle | Open
| Use event logs for deployment monitoring | Open
| Create board.h (constants.h?) | Closed
| Low Power mode | Ongoing | Audio Amp and Codec Analog shut down when not in use
| Support for multiple buddies | Closed
| Volume Control | Closed
| Status LEDs | Closed
| Apply and document consistent coding style | Closed
| Add tracing to Intercom_Buddy (and Controller?) | Rejected
| Factor out tick logic | Closed
| Document object roles | Closed
| Does it make sense to add a fuse to the PCB? | Open
| Document Trace&Debug API | Closed
| Add back button to DeviceDetail activity | Rejected | Against Android policy
| Remember device names in Hola App when they are offine | Closed
| Mention HolaDeviceData class in Hola App Document | Closed
| Battery level check with led bar | Closed
| Improve streaming performance | Closed
| App support for intercom moving to new WiFi network | Closed
| LEDs keep flashing after reset | Closed
| Stabilize not listen -> listen FSM | Closed
| Stabilize startup / WiFi/ cloud connection | Closed
| RateTuning | Closed
| Activate recording when incoming data | Closed
| VU meter | Rejected | Using LED blink instead
| Add FSM diagrams | Closed
| Add WiFi signal strength to cloud API and app | Closed
| Use 5 band equalizer | Closed
| Install stronger speaker | Closed
| Only send EchoReq as keep-alive when no incoming comm. | Rejected | Replaced by simplex keep alive mechanism
| Use exponential back-off for EchoReq | Rejected
| Add permission flag to cloud API to allow recording enable by remote | Open
| Add support for / experiment with ECB mode encryption | Closed
| Experiment with ADPCM 16MHz mode | Closed
| Root cause voice_data message loss and corruption in duplex mode | Closed
| Add percentage widgets for battery and wifi level in app | Closed
| Sync app to latest SDK | Closed
| SX1509 init sometimes fails | Closed | Can't reproduce
| Add DataDump feature | Closed
| Response communication should stop when incoming stops | Closed
| rateTuning is too slow and goes too high and lower | Closed
| Implement voice data retransmission protocol | Open
| Bug: sometimes msg comm goes haywire after speech | Open
| Add SW power down | Closed
| Redo server side design diagram in draw.io | Rejected | Using yuml instead
| Add button to enter setup mode | Closed
| Scalable server architecture | Open
| Buddy config in app takes too long | Closed
| Intercom gets stuck in UDP can't send state | Closed | This happens when internet connection has been lost. Doesn't auto recover.
| Volume Control not working well | Closed
| Hissing, crackling, high pitch noise come from speakers in rest | Closed | Audio Amp shuts down when not in use
| Intercom2 speaker does not work | Closed
| State device name after successful setup | Closed
| Remove photon picture from device setup screen | Closed
| Pop-up on device overview screen if device is ready for setup | Rejected
| Intercom should continue to work even when cloud connection is lost | Closed
| Remove blank screen from app | Rejected
| Move to python3 | Open
| Write Hola User Guide | Open
| Hola App is draining battery | Closed
| Device setup is successful even when password is wrong | Closed
| Keep trying to connect to WiFi when in listening mode | Rejected

## Sheet2
166 | 0.5 | 83
59 | 0.5 | 29.5
59 | 0.5 | 29.5
555 | 0.5 | 277.5
42 | 0.5 | 21
555 | 0.5 | 277.5
52 | 0.5 | 26
150 | 0.5 | 75
13500 | 0.5 | 6750
8388
3500