## Sheet1
| Date: | 2018-01-19
ID | Todos | Status | Notes
| Learn PCB Design | Ongoing | Check Sparkfun guide
| Read Practical Electronics | Ongoing
| Physical UI Design | Ongoing
| Battery charge view in Hola App | Done
| How to respond to Low Battery? | Open
| Antenna | Closed
| Reset Circuit | Open
| Only Forward if mutual buddies | Closed
| Learn OAuth2.0 and RFC6739 | Rejected
| Robustness against server restart | Ongoing | Needs more testing
| Robustness against intercom restart | Ongoing | Needs more testing
| Permant secret key | Closed
| Power switch circuit | Open
| Improve audio quality | Ongoing
| Assume message link is lossy | Closed
| Device setup and configuration via Android App | Closed
| Device setup and configuration via OSX App | Open
| Unique return codes. Use per-module return code base. | Closed
| Echo Cancelling | Open
| Intranet Mode | Open
| Voltage Regulation | Open
| Authentication and Security | Closed
| Battery support | Closed
| Remove my_name setting | Rejected | Keeping my_name because it's local persistent storage. The particle name is kept in the cloud.
| Contribute code library to Particle | Open
| Use event logs for deployment monitoring | Open
| Create board.h (constants.h?) | Closed
| Low Power mode | Open
| Support for multiple buddies | Ongoing | build 3rd setup, test
| Volume Control | Closed
| Status LEDs | Ongoing
| Apply and document consistent coding style | Closed
| Add tracing to Intercom_Buddy (and Controller?) | Rejected
| Factor out tick logic | Closed
| Document object roles | Closed
| Does it make sense to add a fuse to the PCB? | Open
| Document Trace&Debug API | Closed
| Add back button to DeviceDetail activity | Rejected | Against Android policy
| Remember device names in Hola App when they are offine | Done
| Mention HolaDeviceData class in Hola App Document | Done
| Battery level check with led bar | Done
| Improve streaming performance | Ongoing
| App support for intercom moving to new WiFi network | Open
| LEDs keep flashing after reset | Open
| Stabilize not listen -> listen FSM | Closed
| Stabilize startup / WiFi/ cloud connection | Open
| RateTuning | Closed
| Activate recording when incoming data | Closed
| VU meter | Rejected | Using LED blink instead
| Add FSM diagrams | Closed
| Add WiFi signal strength to cloud API and app | Closed
| Used 5 band equalizer | Open
| Install stronger speaker | Open
| Only send EchoReq as keep-alive when no incoming comm. | Open
| Use exponential back-off for EchoReq | Open
| Add permission flag to cloud API to allow recording enable by remote | Open
| Add support for / experiment with ECB mode encryption | Closed
| Experiment with ADPCM 16MHz mode | Ongoing
| Root cause voice_data message loss in duplex mode | Open
| Add percentage widgets for battery and wifi level in app | Closed
| Sync app to latest SDK | Open
| SX1509 init sometimes fails | Ongoing
| Add DataDump feature | Closed
| Response communication should stop when incoming stops | Open
| rateTuning is too slow and goes too high and lowe | Open