## Sheet1
| Date: | 2017-11-28
ID | Todos | Status | Notes
| Learn PCB Design | Ongoing | Check Sparkfun guide
| Read Practical Electronics | Ongoing
| Physical UI Design | Ongoing
| Battery charge view in Hola App | Open
| How to respond to Low Battery? | Open
| Antenna | Open
| Reset Circuit | Open
| Only Forward if mutual buddies | Done
| Learn OAuth2.0 and RFC6739 | Rejected
| Robustness against server restart | Ongoing | Needs more testing
| Robustness against intercom restart | Ongoing | Needs more testing
| Permant secret key | Done
| Power switch circuit | Open
| Improve audio quality | Open
| Assume message link is lossy | Done
| Device setup and configuration via Android App | Done
| Device setup and configuration via OSX App | Open
| Unique return codes. Use per-module return code base. | Open
| Echo Cancelling | Open
| Intranet Mode | Open
| Voltage Regulation | Open
| Authentication and Security | Done
| Battery support | Done
| Remove my_name setting | Ongoing
| Contribute code library to Particle | Open
| Use event logs for deployment monitoring | Open
| Create board.h (constants.h?) | Open
| Low Power mode | Open
| Support for multiple buddies | Ongoing
| Volume Control | Open
| Status LEDs | Ongoing
| Apply and document consistent coding style | Done
| Add tracing to Intercom_Buddy (and Controller?) | Open
| Factor out tick logic | Open | Define a base class?
| Document object roles | Open